## Sheet1
Phase		Begin date		End date	Number of days
Evaluation of different robot configurations			01/11/13	20/11/13	20
3D modelling			21/11/13	05/01/14	46
Assembly			28/01/14	15/02/14	19
Programming: Arduino			16/02/14	20/03/14	33
Programming: Raspberry Pi			03/03/14	25/04/14	54
Programming: Android			07/03/14	27/04/14	52
Report composition			15/07/14	20/09/14	68
Presentation preparation			21/09/14	30/09/14	10
TOTAL DAYS					302
TOTAL HOURS ( 3 hours per day)					906